## WBS Tree
#VALUE! | Fecha | 2025-05-22
| Revision | 1
WBS TREE Diagram
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Task list
#VALUE! |  |  |  |  | Fecha: |  | 2025-05-22
[5 empty] | Rev |  | 1.1
| Project Name | Desarrollo y adaptación de un prototipo de un mecanismo de rotación para los motores de un UAV-VTOL
| Project Manager | Juan Pablo López Batalla
| Date | 2025-05-22
| Version | v1.1
WORK BREAKDOWN STRUCTURE TEMPLATE - TASKS
Task No. | Task Description | Task Owner | Dependency | Resources Needed | Task Status | Cost | Start Date | Estimated Completion | Finish Date | Notes
1 | Initiation Phase
1.1 | Reunión inicial de equipo | Juan Pablo López Batalla | N/A | Sala o espacio de conferencia | Complete | 0 | 2025-05-19 | 3 | 2025-05-22
1.1.1 | Establecimiento de objetivos y alcance | Juan Pablo López Batalla | 1.1 | Sala o espacio de conferencia / Teams | Late |  | 2025-05-19 | 3 | 2025-05-22
1.1.2 | Definición de herramientas colaborativas | Juan Pablo López Batalla | 1.1 | Teams, GitHub | Complete |  | 2025-05-19 | 3 | 2025-05-22
1.1.3 | Identificación inicial de interesados | Juan Pablo López Batalla | 1.1 | Cuestionario | In Progress |  | 2025-05-20 | 3 | 2025-05-23
1.1.4 | Redacción del acta de constitucion | Kenya Zuñiga Ramos | 1.1.3 | Teams, GitHub, Word | In Progress |  | 2025-05-22 | 10 | 2025-06-01
2 | Planning Phase
2.1 | Elaboración de la EDT | Juan Pablo López Batalla | 1.1.3 | Teams, GitHub, Word | In Progress |  | 2025-05-20 | 10 | 2025-05-30
2.2 | Identificación de requerimientos tecnicos | Cesar López Vargas | 1.1.3 | EDT, cuestionario, internet | In Progress |  | 2025-05-22 | 2 | 2025-05-24
2.3 | Planeación del cronograma y tareas | Juan Pablo López Batalla | 1.1.3 | Github, Excel | In Progress |  | 2025-05-22 | 3 | 2025-05-25
2.3.1 | Asignación de tareas | Juan Pablo López Batalla | 1.1.3 | Github, Excel | In Progress |  | 2025-05-22 | 3 | 2025-05-25
2.3.2 | Definición de tiempos y entregas | Juan Pablo López Batalla | 1.1.3 | Github, Excel | In Progress |  | 2025-05-22 | 3 | 2025-05-25
2.4 | Identificación y gestión de riesgos | Carlos Hernandez Arteaga | 1.1 |  | Assigned
2.5 | Planeación de la comunicación del equipo | Kenya Zuñiga Ramos | 1.1.2 |  | Assigned
2.6 | Estimación y asignación del presupuesto | Santiago Vargas Ramirez | 1.1.4 |  | Assigned
2.7 | Plan de adquisiciones | Carlos Hernandez Arteaga | 2.6 |  | Assigned
3 | Execution Phase
3.1 | Diseño Técnico | Juan Pablo López Batalla | 2.4 |  | Assigned
3.1.1 | Investigación y anásis de mecanismos similares | Carlos Hernandez Arteaga | 2.4 |  | Assigned
3.1.2 | Diseño conceptual del mecanismo | Cesar López Vargas | 2.3.2 |  | Assigned
3.1.3 | Selección del diseño final | Juan Pablo López Batalla | 3.1.2 |  | Assigned
3.1.4 | Modelado CAD del mecanismo | Juan Pablo López Batalla | 3.1.3 |  | Assigned
3.1.4.1 | Simulación de movimiento y esfuerzos | Santiago Vargas Ramirez | 3.1.4 |  | Assigned
3.1.4.2 | Optimización del diseño | Juan Pablo López Batalla | 3.1.4.1 |  | Assigned
3.1.5 | Exportación de planos y renders | Santiago Vargas Ramirez | 3.1.4.2 |  | Assigned
3.1.6 | Revisión técnica interna del modelo | Cesar López Vargas | 3.1.4.2 |  | Assigned
3.2 | Prototipado físico | Santiago Vargas Ramirez | 3.1.6 |  | Assigned
3.2.1 | Selección de materiales y componentes | Kenya Zuñiga Ramos | 3.1.6 |  | Assigned
3.2.2 | Evaluación de métodos de fabricación | Cesar López Vargas | 3.1.6 |  | Assigned
3.2.3 | Generación de archivos para fabricación | Santiago Vargas Ramirez | 3.1.6 |  | Assigned
3.2.4 | Adquisición de materiales y componentes | Carlos Hernandez Arteaga | 3.2.1 |  | Assigned
3.2.5 | Fabricación de piezas | Cesar López Vargas | 3.2.4 |  | Assigned
3.2.6 | Montaje del prototipo | Santiago Vargas Ramirez | 3.2.5 |  | Assigned
3.2.7 | Verificación del ensamble | Juan Pablo López Batalla | 3.2.6 |  | Assigned
3.2.8 | Documentación del proceso | Kenya Zuñiga Ramos | 3.2.7 |  | Assigned
4 | Control Phase
4.1 | Pruebas y validación | Cesar López Vargas | 3.2.7 |  | Assigned
4.1.1 | Definición de criterios de prueba | Juan Pablo López Batalla | 4.1 |  | Assigned
4.1.2 | Ejecución de pruebas funcionales | Santiago Vargas Ramirez | 4.1 |  | Assigned
4.1.3 | Análisis de resultados | Carlos Hernandez Arteaga | 4.1.2 |  | Assigned
4.1.4 | Iteración del diseño (si es necesario) | Santiago Vargas Ramirez | 4.1.3 |  | Assigned
4.1.5 | Validación técnica final | Juan Pablo López Batalla | 4.1.4 |  | Assigned
4.1.6 | Registro audiovisual de pruebas | Kenya Zuñiga Ramos | 4.1.5 |  | Assigned
5 | Close Phase
5.1 | Compilación de entregables | Cesar López Vargas | 4.1.6 |  | Assigned
5.1.1 | Redacción del informe final | Kenya Zuñiga Ramos | 4.1.6 |  | Assigned
5.1.2 | Organización del repositorio del proyecto | Kenya Zuñiga Ramos | 5.1 |  | Assigned
5.2 | Reunión de cierre de proyecto | Juan Pablo López Batalla | 4.1.6 |  | Assigned
5.3 | Presentación de resultados | Cesar López Vargas | 5.1.2 |  | Assigned
5.4 | Archivo y respaldo de información | Carlos Hernandez Arteaga | 5.3 |  | Assigned